## Slide 1: FESTIM Fellowship Work Plan E. Yildirim

## Slide 2: Overview
Summer Cohort starting in mid-June
20 hrs/week expected commitment
2 trips favored for start and mid progress, with possible final wrap up trip at the end

## Slide 3: Structure
Stage | Weeks | Focus | Status
Stage 1 | 1-4 | Pebble Model Refinement -- validated, reproducible FESTIM model of tritium release from lithium ceramics | Core
Stage 2 | 5-8 | Helium Purge Loop System Model -- system-level TES model integrating pebble outputs into purge loop behaviour | Core
Stage 3 | 9-10 (conditional) | Plant-Scale Surrogate -- reduced-order model for integration into PathSim/FactorySim fuel cycle frameworks | Stretch only

## Slide 4: Stage 1 – Pebble Model Evaluation
Week | Theme | Key Activities | Outcome
1 | Model Audit and Onboarding | Review existing pebble model against FESTIM best practices. Identify parameter gaps. Establish reproducibility standards: version control, run configuration, output structure. Initial engagement with FESTIM development team. | Documented model audit; parameter gap list; reproducibility baseline established
2 | Physics Refinement | Refine temperature-dependent transport parameters. Improve sweep gas condition sensitivity. Incorporate irradiation history effects. Work with the team on best-practice parameterisation approaches. | Updated model with improved physics fidelity; parameters documented with sources and confidence levels
3 | Uncertainty and Experimental Coupling | Apply team-recommended uncertainty handling approaches. Structure model outputs for comparison against measured data. Align output formats with H2 laboratory rig data. Review LIBRA experimental setup experience. | Uncertainty framework in place; model structured and ready to receive experimental data when available
4 | Benchmarking and Stage 1 Sign-off | Benchmark against published lithium ceramic release data. Document validation status and remaining gaps. | Benchmarked pebble-scale FESTIM model; benchmarking report; Stage 1 deliverable complete

## Slide 5: Stage 2 – Pure Loop Model
Week | Theme | Key Activities | Outcome
5 | Architecture and Setup | Design helium purge loop model structure, small volume simulation. Understand FESTIM best practice for multi-component system-scale simulations. Define purge loop geometry and component definitions. | Purge loop architecture documented; FESTIM system model scaffolding in place
6 | Core Model Build | Implement conventional sweep gas circuit with getter bed extraction. Model tritium partial pressure evolution blanket and purge loop. Frame effects of pebble mobilization (gravity fed). | Working purge loop model; baseline tritium partial pressure profiles generated
7 | Sensitivity and Operating Conditions | Parametric study of extraction efficiency vs. operating conditions. Assess effects of pebble bed packing and network geometry on bulk release behaviour. Assess flow conditions for pebbles themselves. | Sensitivity results; identification of key design levers for TES operating conditions
8 | Cycling Simulations and Stage 2 Sign-off | Run transient cycling simulations to assess pebble performance under load-following conditions. Package results for Infinity II TES design trade studies. | Cycling simulation results; Stage 2 deliverable packaged for the Infinity II design team

## Slide 6: Stage 3
PathSim / Factory Style Model
Looking at how upstream and downstream systems interplay
  E.g. Blanket, Extraction, HX
Some of these could be analytical solutions, or FESTIM models themselves
Interesting effects would be:
  Recirculating pebble tritium concentration
  Gettering / permeating downstream
  Dynamic control

## Slide 7: Visualization
1D Model verified vs. 3D for pebble release
Stage 1

## Slide 8: Visualization
1D Model verified vs. 3D for pebble release
Sweep Gas + Pebble Recirc.
Stage 1
Stage 2

## Slide 9: Visualization
1D Model verified vs. 3D for pebble release
Tritium Extraction
Heat Exchanger
Stage 1
Stage 2
Stage 3
Sweep Gas + Pebble Recirc.

## Slide 10: How FESTIM will be used

## Slide 11: Utilization in T1E workflow
FESTIM will be integrated into system where there are no existing analytical solutions, and transient work is desired
The fellowship will allow us to build this up for the pebbles, but also give us the workflow for other systems
These models will always need to be feeding process models at the higher level, so that integration will be key
Similarly – the length scales of the components themselves e.g. blankets, is very large, therefore understand how to translate through the length scales will be key, in addition to the time scales

## Slide 13: New Section
Use this slide to introduce a new section or topic.

## Slide 14: New Section

## Slide 15: General Content Slide
Fill this slide with your content
  Press tab for a sub-bullet
  Create a new sub-bullet then press and hold shift + tab…
…To come back here!

## Slide 16: Text-only Slide
Is your slide only text? Want it to look cool?
  Use this slide when you have a wall of text but need some visual interest

## Slide 17: Content + Subtitle Slide
Now expand upon the topic in the subtitle, etc.
This is a subtitle about the content of this slide

## Slide 18: Content + Images Slide
Fill this slide with you content
  Press tab for a sub-bullet
  Create a new sub-bullet then press and hold shift + tab…
…To come back here!

## Slide 19: Content + Image Slide
When you only have one image, try to format it like this
You can use this slide and just change the image
  Select the image on the right
  Go to “Picture Format” in the upper menu
  Toward the left-hand side look for “Change Picture”
  Select “From a File…” and add your own image

## Slide 20: Highlight Image + Notes
Use a large photo to emphasize your point
To change the image on this slide:
  Select the image on the right
Go to “Picture Format” in the upper menu
  Toward the left-hand side look for “Change Picture”
  Select “From a File…” and add your own image

## Slide 21: Timeline Slide
2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2030s…
Recap past events and accomplishments
State quick facts
Or highlight an upcoming milestone

## Slide 22: Highlight Slide 1
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things

## Slide 23: Highlight Slide 2
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things
Milestone #1
List things
More things
Even more things

## Slide 24: Big Ideas
List things
More things
Even more things
List things
More things
Even more things
Idea #1
Idea #2

## Slide 25: Big Ideas
List things
More things
Even more things
Idea #1
List things
More things
Even more things
Idea #2
List things
More things
Even more things
Idea #3
Add the major takeaway at the bottom if applicable

## Slide 26: Big Ideas
List things
More things
Even more things
Idea #1
Idea #2

## Slide 27: Processes
List things
Show images
List things
Show images
List things
Show images
List things
Show images

## Slide 28: Meet Your Team
John Smith
Jane Doe
Person #1
Person #2
Person #3
Title, ex) Systems Engineer
Title, ex) Marketing and Communications Specialist
Title
Title, ex) CTO
Title, ex) Director, Fuel Cycle
Brief description or bullet points about the individual
Brief description or bullet points about the individual

## Slide 29: Need more support?
Matt Miles
Celeste Cubbage
Sarah Clark
SVP, Marketing and External Affairs
Marketing and Communications Specialist
Title
Go to the MarComm SharePoint Page for past decks and ideas
  Check out all the resources on that page while you’re there
Reach out to a member of MarComm if you still have questions remaining
If you need help:

## Slide 30: Images Approved to Use – Infinity One

## Slide 31: Images Approved to Use – Magnet Zero

## Slide 32: Our Logos

## Slide 33: Thank you!